## DevOps Task List
Task | Ownership | Start Date | End Date | Status | Dependency | Remarks
Feature: SCM(Source Code Management)
Install Git VCS on Windows Server 2022. | Prabha | 2024-08-06 | 2024-08-06 | Completed | Chandra
Set up Git PATH for both Admin and RDP Users. | Prabha | 2024-08-06 | 2024-08-06 | Completed | Chandra
Configure Git for Admin and RDP Users. | Prabha | 2024-08-07 | 2024-08-07 | Completed | Chandra
Create Gitea accounts for both Admin and RDP Users. | Prabha | 2024-08-07 | 2024-08-07 | Completed | Chandra
Perform SSH Authentication for both Admin and RDP Users. | Prabha | 2024-08-08 | 2024-08-09 | Completed | Chandra
Prepare a hands-on document for SCM implementation. | Prabha | 2024-08-09 | 2024-08-10 | Completed | Chandra
Feature: Server Set Up Notes
Prepare hands-on notes about the Server Set-Up process, covering all necessary configurations and settings. | Prabha | 2024-08-10 | 2024-08-11 | Completed | Chandra
Feature: DevOps Set Up Notes
Prepare hands-on notes detailing the DevOps Set-Up process, including tools, configurations, and environments. | Prabha | 2024-08-10 | 2024-08-11 | Completed | Chandra
Feature: DevOps Tools Evaluation & Finalization
Prepare a comparison for each CI/CD tool, evaluating their features, pros, cons, and suitability for the project. | Prabha | 2024-08-12 | 2024-08-13 | Completed | Chandra
Finalize the selection of DevOps tools based on the evaluation. | Prabha | 2024-08-13 | 2024-08-14 | In Progress | Chandra
Feature: CI(Continuous Integration) Implementation
Learn about implementing Jenkins for Continuous Integration. | Prabha | 2024-08-13 | 2024-08-14 | Not Yet Started | Chandra
Install Jenkins on Windows Server 2022. | Prabha | 2024-08-14 | 2024-08-16 | Not Yet Started | Chandra
Learn about Docker for containerization. | Prabha | 2024-08-19 | 2024-08-20 | Not Yet Started | Chandra
Install Docker on Windows Server 2022. | Prabha | 2024-08-20 | 2024-08-21 | Not Yet Started | Chandra
Feature: CD(Continuous Deployment) Implementation
Learn about Ansible for Continuous Deployment. | Prabha | 2024-08-21 | 2024-08-22 | Not Yet Started | Chandra
Install Ansible on Windows Server 2022. | Prabha | 2024-08-22 | 2024-08-23 | Not Yet Started | Chandra
Learn about Chef for Configuration Management. | Prabha | 2024-08-26 | 2024-08-27 | Not Yet Started | Chandra
Install Chef on Windows Server 2022. | Prabha | 2024-08-27 | 2024-08-28 | Not Yet Started | Chandra
Learn about Kubernetes for managing Docker containers. | Prabha | 2024-08-28 | 2024-08-29 | Not Yet Started | Chandra
Install Kubernetes on Windows Server 2022. | Prabha | 2024-08-29 | 2024-08-30 | Not Yet Started | Chandra
Complete the CI/CD pipeline implementation on Windows Server 2022. | Prabha | 2024-08-30 | 2024-09-02 | Not Yet Started | Chandra
Verify the entire SCM and CI/CD process for the application, ensuring that everything works correctly. | Prabha | 2024-09-03 | 2024-09-04 | Not Yet Started | Chandra
Feature: JIRA with GIT Integration
Learn about implementing JIRA with Git integration. | Prabha | 2024-08-23 | 2024-08-24 | Not Yet Started | Chandra
Integrate JIRA with Git to streamline issue tracking with source code management. | Prabha | 2024-08-24 | 2024-08-26 | Not Yet Started | Chandra
Feature: Implementation Features
Implement Git Versioning and Tagging for maintaining versions of the application and managing releases. | Prabha | 2024-08-24 | 2024-08-26 | Not Yet Started | Chandra
Feature: Release Management

## Frontend Task List
Tasks | Ownership | start date | end date | status | Remarks | Dependency
Home page creation
Layout page creation | Kanakadurga | 27-07-2024 | 27-07-2024 | Completed
Get started button | Kanakadurga | 27-07-2024 | 27-07-2024 | Completed
Auth Verification
To prepare token restriction functionality | Aarthi | 2024-08-10 | 2024-08-13 | Completed
Signin page creation
sign in component | Kanakadurga | 29-07-2024 | 29-07-2024 | Completed
sign in page functionality | Kanakadurga | 29-07-2024 | 29-07-2024 | Completed
To apply login functionality | Aarthi |  |  | Completed
To set icon for login input fields | Aarthi |  |  | Completed
To apply pasword eye icon functionality | Aarthi |  |  | Completed
To apply signout functionality to all the dashboad | Aarthi |  |  | Completed
Header component
header creation | Kanakadurga | 30-07-2024 | 30-07-2024 | Completed
theme setup
theme provider component | Kanakadurga | 31-07-2024 | 2024-01-08 | Completed
theme functionality using redux | Kanakadurga | 31-07-2024 | 2024-01-08 | Completed
setting up store for theme | Kanakadurga | 31-07-2024 | 2024-01-08 | Completed
notification bell
notificiation popup creation | Kanakadurga | 2024-02-08 | 2024-02-08 | Completed
Dashboard component
dashboard component with all tabs | Kanakadurga | 2024-05-08 | 2024-05-08 | Completed
sidebar creation | Kanakadurga | 2024-05-08 | 2024-05-08 | Completed
chatwindow and text bar creation | Kanakadurga | 2024-06-08 | 2024-08-08 | Completed
adding more details function to chat window | Kanakadurga | 2024-06-08 | 2024-09-08 | Completed
More details popup creation | Kanakadurga | 2024-06-08 | 2024-09-08 | Completed
scroll bar to chat window and text area | Kanakadurga | 2024-06-08 | 2024-09-08 | Completed
Super admin dashboard
Super admin sidebar | Kanakadurga | 2024-10-08 | 2024-10-08 | Completed
propmt and response function for super admin dashboard | Aarthi | 2024-08-14 | 2024-08-15 | Not Yet Started
To apply file upload function with extention restriction in super admin dashboard | Aarthi | 2024-08-15 | 2024-08-16 | Not Yet Started
To add more details functionality in super admin dashboard | Aarthi | 2024-08-21 | 2024-08-22 | Not Yet Started
To prepare notifiaction icon functionality | Aarthi | 2024-08-19 | 2024-08-20 | Not Yet Started
user management window
add user popup | Kanakadurga | 2024-12-08 | 14/08/2024 | Completed
edit user popup | Kanakadurga | 2024-12-08 | 14/08/2024 | Completed
delete user popup | Kanakadurga | 2024-12-08 | 14/08/2024 | Completed
datatable for user management | Kanakadurga | 2024-12-08 | 14/08/2024 | Completed
To add table data dynamically in user manage ment page | Aarthi | 2024-08-22 | 2024-08-23 | Not Yet Started
To apply functionality for popup edit and delete within table data | Aarthi | 2024-08-23 | 2024-08-24 | Not Yet Started
To create edit functionality in user management page | Aarthi | 2024-08-24 | 2024-08-26 | Not Yet Started
To prepare delete functionality for user management page | Aarthi | 2024-08-26 | 2024-08-27 | Not Yet Started
To prepare add user popup functionality in user management page | Aarthi | 2024-08-27 | 2024-08-28 | Not Yet Started
To prepare post call functionality for add user page | Aarthi | 2024-08-28 | 2024-08-29 | Not Yet Started
requested files window
approve and reject popup | Kanakadurga | 2024-12-08 | 14/08/2024 | Completed
datatable for requested files | Kanakadurga | 2024-12-08 | 14/08/2024 | Completed
To add table data dynamically in requested file page | Aarthi | 2024-08-29 | 2024-08-30 | Not Yet Started
To apply functionality for edit and delete within table data in requested file | Aarthi | 2024-09-02 | 2024-09-03 | Not Yet Started
To create edit functionality in requested file page | Aarthi | 2024-09-03 | 2024-09-04 | Not Yet Started
To prepare delete functionality for requested file page | Aarthi | 2024-09-04 | 2024-09-05 | Not Yet Started
To prepare view file functionality | Aarthi | 2024-09-05 | 2024-09-06 | Not Yet Started
To create popup with file details functionality | Aarthi | 2024-09-06 | 2024-09-09 | Not Yet Started
to prepare accept and reject function | Aarthi | 2024-09-09 | 2024-09-10 | Not Yet Started
admin dashboard
admin sidebar and dashboard creation | Kanakadurga | 16/08/2024 | 16/08/2024 | Completed
propt and response function for admin dashboard | Aarthi | 2024-08-16 | 2024-08-16 | Not Yet Started
To apply file upload function with extention restriction in admin dashboard | Aarthi | 2024-08-19 | 2024-08-20 | Not Yet Started
To add more details functionality in admin dashboard | Aarthi | 2024-08-20 | 2024-08-21 | Not Yet Started
user dashboard
user dashboard and sidebar creation | Kanakadurga | 16/08/2024 | 16/08/2024 | Completed
propt and response function for user dashboard | Aarthi | 2024-08-16 | 2024-08-16 | Not Yet Started
To apply file upload function with extention restriction in user dashboard | Aarthi | 2024-08-19 | 2024-08-20 | Not Yet Started
To add more details functionality in user dashboard | Aarthi | 2024-08-20 | 2024-08-21 | Not Yet Started
Private header component for admin and user
private header for admin and user | Kanakadurga | 19/08/2024 | 19/08/2024 | Completed
Profile page creation
profile page for super admin , admin and user | Kanakadurga | 19/08/2024 | 19/08/2024 | Completed
about page creation
need content for about and home page | [5 empty] | Varphi team
Flash message component creation
To add flash message functionality | Aarthi | 2024-09-10 | 2024-09-11 | Not Yet Started

## Backend Task List
Tasks | Ownership | start date | end date | status
Feature: Authentication and authorization
To create a route to login | Akhilesh |  |  | Completed
To create a table for user login in mongoDB | Akhilesh |  |  | Completed
To add a function to create a JWT token (encode and decode) | Akhilesh |  |  | Completed
To add a function for Oauth2 authentication | Akhilesh |  |  | Completed
Write a function for authorizing the user to access users to the chat interface | Akhilesh | 2024-08-12 | 2024-08-13 | In progress
Feature: Handle Super Admin, Admin and User in Backend
To create a route to super admin, admin and user | Akhilesh | 2024-08-14 | 2024-08-14 | Not Yet Started
create a table for Admin notification in mongoDB | Akhilesh | 2024-08-19 | 2024-08-19 | Not Yet Started
Write a function to store the notification related to user file request details on database | Akhilesh | 2024-08-20 | 2024-08-21 | Not Yet Started
create a table for User notification in mongoDB | Akhilesh | 2024-08-22 | 2024-08-22 | Not Yet Started
Write a function to store the notification related to admin acceptance details on database | Akhilesh | 2024-08-23 | 2024-08-24 | Not Yet Started
To create a route for uploaded files | Akhilesh | 2024-08-26 | 2024-08-26 | Not Yet Started
Write a function to send the uploaded files to the ML to store in vectorDB | Akhilesh | 2024-08-27 | 2024-08-27 | Not Yet Started
Write a function to send the response back to the frontend | Akhilesh | 2024-08-28 | 2024-08-29 | Not Yet Started
To create a route for prompts | Akhilesh | 2024-08-30 | 2024-08-30 | Not Yet Started
Write a function to send the query to ML for getting the response for the query | Akhilesh | 2024-09-02 | 2024-09-02 | Not Yet Started
Write a function to forward the response back to the frontend including details | Akhilesh | 2024-09-03 | 2024-09-03 | Not Yet Started
To create a route for user uploaded files | Akhilesh | 2024-09-04 | 2024-09-04 | Not Yet Started
Write a function to accept or reject user uploaded files | Akhilesh | 2024-09-05 | 2024-09-05 | Not Yet Started
Feature: Handling user management
To create a route for adding the users | Akhilesh | 2024-09-06 | 2024-09-06 | Not Yet Started
Write a function to handle inserting the users to the mongoDB | Akhilesh | 2024-09-09 | 2024-09-09 | Not Yet Started
To create a route for editing the users | Akhilesh | 2024-09-10 | 2024-09-10 | Not Yet Started
Write a function to handle update the users in the mongoDB | Akhilesh | 2024-09-11 | 2024-09-11 | Not Yet Started
To create a route for deleting the users | Akhilesh | 2024-09-12 | 2024-09-12 | Not Yet Started
Write a function to handle delete the users in the mongoDB | Akhilesh | 2024-09-13 | 2024-09-13 | Not Yet Started
Feature: Handling Multiple users
To make the functions asynchronous for handling multiple users | Akhilesh | 2024-09-14 | 2024-09-18 | Not Yet Started